## Master
Greater Santa Fe Fireshed Projects
UPDATED 10/17/2017
|  |  | Funding Sources | [5 empty] | Acreage
Project Name | Project Type | Project Status | Name of Source #1 | Amount of Source #1 | Name of Source #2 | Amount of Source #2 | Total Funding | Funding Expended | Target Acres | Completed Acres | Ownership | Acronyms
Aztec Springs (SFFD) Phase 1 | Thin and pile | Completed | STB | 115517 | - | 0 | 115517 | 99762 | 90 | 70 | City of Santa Fe/TNC | STB - State Severance Tax Bonds
SE Santa Fe Corridor NFL (SFPSWCD & NMSF) | Thin - WUI | NTP granted | NFL | 261250 | - | 0 | 261250 | 0 | 200 | 0 | Private | NFL - Hazardous Fuels Reduction on Non-federal Lands (USFS flow-through grant)
Hyde Memorial State Park (NMSF) | Thin/pile/burn | Ongoing | NFL | 175450 | NFL | 87065 | 262515 | 106102.88 | 110 | 90 | State
Glorieta Corridor (NMSF) | Thin and chip | Ongoing | STB | 120000 | - | 0 | 120000 | 116474 | 100 | 85 | State | STB - State Severance Tax Bonds
Pueblo of Tesuque - Aspen Ranch 2010-2016 | thin/pile | completed | BIA | 205619 | 0 | 0 | 205619 | 205619 | 125 | 125 | Pueblo | BIA - Bureau of Indian Affairs
Pueblo of Tesuque - Aspen Ranch 2017 - Present | retreat/pile/wood harvest | Sept.2017-Sept 2018 | BIA | 63552 | 0 | 0 | 63552 | 0 | 57 | 0 | Pueblo
Pueblo of Tesuque - Box Canyon | thin/pile/wood harvest | Sept.2017-Sept.2019 | USFWS (2017) | 199999 | 0 | 0 | 199999 | 0 | 100 | 0 | Pueblo | USFWS - US Fish & Wildlife Service
Pueblo of Tesuque - Reserved Treaty Rights Lands | retreat/thin/pile | Sept. 2017-Sept.2018 | BIA (2017) | 327028 | 0 | 0 | 327028 | 0 | 62 | 0 | Pueblo
RTRL - Aspen Ranch | retreat/pile/wood harvest | Sept. 2017-Sept.2018 | BIA | 0 | 0 | 0 | 0 | 0 | 23 | 10 | Pueblo
RTRL - Vigil Grant | thin/pile/wood harvest | Sept. 2017-Sept.2018 | BIA | 0 | - | 0 | 0 | 0 | 39 | 0 | Pueblo
La Cueva Fuelbreak Block A | Thin and pile | Completed | USFS | 200000 | - | 0 | 200000 | 200000 | 239 | 239 | USFS | USFS - US Forest Service internal funds
La Cueva Fuelbreak Block E | Thin and pile | Ongoing | CapOutlay Watershed | 213000 | - | 0 | 213000 | 0 | 133 | 10 | USFS
Hyde Park Restoration Project (SFNF) | TBD | in NEPA | USFS | 0 | - | 0 | 0 | 0 | 0 | 0 | USFS
Pacheco Canyon (SFNF) | TBD | in NEPA | USFS | 31832 | - | 0 | 31832 | 0 | 0 | 0 | USFS
Private Lands NMAC (Forest Guild) | Thin and var slash trmts | Completed | NMAC/BLM | 30400 | - | 0 | 30400 | 0 | 40 | 38 | Private | NMAC - NM Association of Counties grant (BLM funds)
Fireshed LSR Project (SFPSWCD & NMSF) | Thin and chip | In contracting | LSR | 293210 | - | 0 | 293210 | 0 | 200 | 0 | Private/non-federal | LSR - Landscape Scale Restoration (USFS grant to State Forestry)
Aztec Springs, Phase 2-3 | Thin/pile/burn | 0 | CapOutlay Watershed | 59000 | NFL | 286507 | 345507 | 0 | 175 | 0 | City/TNC/ Audubon
Pecos Canyon Watershed Project (NMDGF and NM State Parks) | ? | Proposed - pending land transfer | N/A | 0 | N/A | 0 | 0 |  | 0 | 0 | NMDGF
Proposed Project #2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Proposed Project #3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Proposed Project #4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Proposed Project #5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Total: |  |  |  | 2295857 |  | 373572 | 2669429 | 727957.88 | 1693 | 667

## Funded Projects
Project Name & Sponsor(s) | Funding Source #1 | Amount Funded | Funding Source #2 | Amount Funded2 | Total Funding | Project Status | Amount Expended | Percent Expended | Target Acres | Completed Acres | Percent Completed | Project Type | Ownership | Project Manager (contact)
Aztec Springs (SFFD) Phase 1 | STB | 115517 | - | 0 | 115517 | Completed | 99762 | 86.36% | 90 | 70 | 77.78% | Thin and pile | City of Santa Fe/TNC | Porfirio Chavarria
SE Santa Fe Corridor NFL (SFPSWCD & NMSF) | NFL | 261250 | - | 0 | 261250 | NTP granted | 0 | 0% | 200 | 0 | 0% | Thin - WUI | Private | Jose Varela Lopez/NMSF
Hyde Memorial State Park (NMSF) | NFL | 175450 | NFL | 87065 | 262515 | Ongoing | 106102.88 | 40.42% | 110 | 90 | 81.82% | Thin/pile/burn | State | George Smithson
Glorieta Corridor (NMSF) | STB | 120000 | - | 0 | 120000 | Ongoing | 116474 | 97.06% | 100 | 85 | 85% | Thin and chip | State | Carmen Austin
Pueblo of Tesuque - Aspen Ranch 2010-2016 | BIA | 205619 |  |  | 205619 | completed | 205619 | 100% | 125 | 125 | 100% | thin/pile | Pueblo | Ryan Swazo-Hinds
Pueblo of Tesuque - Aspen Ranch 2017 - Present | BIA | 63552 |  |  | 63552 | Sept.2017-Sept 2018 | 0 | 0% | 57 |  | 0% | retreat/pile/wood harvest | Pueblo | Michael Martinez/Ryan Swazo-Hinds
Pueblo of Tesuque - Box Canyon | USFWS (2017) | 199999 |  |  | 199999 | Sept.2017-Sept.2019 | 0 | 0% | 100 | 0 | 0% | thin/pile/wood harvest | Pueblo | Ryan Swazo-Hinds
Pueblo of Tesuque - Reserved Treaty Rights Lands | BIA (2017) | 327028 |  |  | 327028 | Sept. 2017-Sept.2018 | 0 | 0% | 62 | 0 | 0% | retreat/thin/pile | Pueblo | Michael Martinez
RTRL - Aspen Ranch | BIA | 0 |  |  | 0 | Sept. 2017-Sept.2018 | 0 | #DIV/0! | 23 | 10 | 43.48% | retreat/pile/wood harvest | Pueblo | Michael Martinez
RTRL - Vigil Grant | BIA | 0 | - |  | 0 | Sept. 2017-Sept.2018 | 0 | #DIV/0! | 39 | 0 | 0% | thin/pile/wood harvest | Pueblo | Michael Martinez
La Cueva Fuelbreak Block A | USFS | 200000 | - | 0 | 200000 | Completed | 200000 | 100% | 239 | 239 | 100% | Thin and pile | USFS | Steve Romero/Michael Lujan
La Cueva Fuelbreak Block E | CapOutlay Watershed | 213000 | - | 0 | 213000 | Ongoing | 0 | 0% | 133 | 10 | 7.519% | Thin and pile | USFS | Steve Romero/Michael Lujan
Hyde Park Restoration Project (SFNF) | USFS | 0 | - | 0 | 0 | in NEPA | 0 | #DIV/0! |  |  | #DIV/0! | TBD | USFS | Sandy Hurlocker/Hannah Bergemann
Pacheco Canyon (SFNF) | USFS | 31832 | - | 0 | 31832 | in NEPA | 0 | 0% |  |  | #DIV/0! | TBD | USFS | Sandy Hurlocker/Hannah Bergemann
Private Lands NMAC (Forest Guild) | NMAC/BLM | 30400 | - | 0 | 30400 | Completed | 0 | 0% | 40 | 38 | 95% | Thin and var slash trmts | Private | Eytan Krasilovsky
Fireshed LSR Project (SFPSWCD & NMSF) | LSR | 293210 | - | 0 | 293210 | In contracting | 0 | 0% | 200 | 0 | 0% | Thin and chip | Private/non-federal | Jose Varela Lopez/Susan Rich (temp)
Aztec Springs, Phase 2-3 | CapOutlay Watershed | 59000 | NFL | 286507 | 345507 | NTP pending | 0 | 0% | 175 | 0 | 0% | Thin/pile/burn | City/TNC/ Audubon | Todd Haines
|  |  | - | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
|  |  |  | 0 | 0 |  |  | #DIV/0! |  |  | #DIV/0!
Total | 0 | 2295857 | 0 | 373572 | 2669429 |  | 727957.88 | 27.27% | 1693 | 667 | 39.4%
Note on G1: Author: Ongoing, Completed
Note on G6: Author: Sept 2010 - Sept 2016
Note on J8: Author: 50 acres w/ 50 match = 100 acres
Note on A9: Author: RTRL will fund both Aspen Ranch and Vigil Grant

## Proposed Projects
Project Name | Amount Request/Award | Funding Source | Proposal Status | Match Amount | Match Source | Leverage Amount | Leverage Source | Total Project Cost | Target Acres | Project Type | Ownership | Project Manager (contact)
Pecos Canyon Watershed Project (NMDGF and NM State Parks) | 0 | N/A | Proposed - pending land transfer | 0 | N/A | 0 | N/A | 0 | ? | ? | NMDGF | ?
Proposed Project #2 | [7 empty] | 0
Proposed Project #3 | [7 empty] | 0
Proposed Project #4 | [7 empty] | 0
Proposed Project #5 | [7 empty] | 0
Proposed Project #6 | [7 empty] | 0
Proposed Project #7 | [7 empty] | 0
Proposed Project #8 | [7 empty] | 0
Proposed Project #9 | [7 empty] | 0
Proposed Project #10 | [7 empty] | 0
Proposed Project #11 | [7 empty] | 0
Proposed Project #12 | [7 empty] | 0
etc. | [7 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total | 0 |  |  | 0 |  | 0 |  | 0 | 0
Note on D1: Author: Proposal submitted, Pending NTP